## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a developer,I want to develop a bug submission module | Must | None | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-002 | As a developer,I want users to submit bug reports for AI analysis | Must | US-001 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-003 | As a developer,I want to support direct paste for bug reports | Must | US-002 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-004 | As a developer,I want to support file upload for bug reports,stack traces,and error logs | Must | US-003 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-005 | As a developer,I want to build a historical defect knowledge base. | Must | US-004 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-006 | As a developer,I want to integrate Mozilla,Apache,and Eclipse datasets. | Should | US-005 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-007 | As a developer,I want to implement document chunking for the rag pipeline. | Must | US-006 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-008 | As a developer,I want to generate embeddings for bug report | Must | US-007 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-009 | As a developer,I want to create a vector store index for semantic retrieval. | Must | US-008 | Vaishnavi Goud | Done
Sprint 1 | Sprint 1 | US-010 | As a developer,I want to validate the Rag retrieval pipeline | Should | US-009 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-011 | As a developer, I want to build a bug triage agent. | Must | None | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-012 | As a developer, I want the triage agent to classify bugs by severity (Critical, High, Medium, Low). | Must | US-011 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-013 | As a developer, I want the triage agent to assign bug priority, affected component, confidence score, and reasoning. | Must | US-012 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-014 | As a developer, I want to build a log analysis agent for bug reports. | Must | US-013 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-015 | As a developer, I want to parse stack traces and error messages to identify exception types and failure points. | Must | US-014 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-016 | As a developer, I want the log analysis agent to identify the affected code path and generate structured output. | Must | US-015 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-017 | As a developer, I want the log analysis agent to identify the affected code path and generate structured output. | Must | US-016 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-018 | As a developer, I want the triage and log analysis outputs to be passed as context to downstream agents. | Should | US-017 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-019 | As a developer, I want to validate the triage and log analysis agents using varied bug report formats and seeded datasets. | Must | US-018 | Vaishnavi Goud | Done
Sprint 2 | Sprint 2 | US-020 | As a developer, I want to evaluate agent accuracy across different error types and validate the overall analysis pipeline. | Should | US-019 | Vaishnavi Goud | Done
Sprint 3 | Sprint 3 | US-021 | As a developer, I want to view all bug analysis results in one dashboard. | Must | US-005 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-022 | As a developer, I want to view bug summary and triage results. | Must | US-021 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-023 | As a developer, I want to view log analysis results. | Must | US-021 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-024 | As a developer, I want to view risk assessment details. | Must | US-021 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-025 | As a developer, I want to view root cause analysis results. | Must | US-021 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-026 | As a developer, I want to view duplicate bug detection results. | Should | US-025 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-027 | As a developer, I want to view recommended remediation and fixes. | Must | US-025 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-028 | As a developer, I want to view historical solutions for similar bugs. | Should | US-003 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-029 | As a developer, I want to see complete analysis information without unknown values. | Must | US-021 | Vaishnavi Goud | Closed
Sprint 3 | Sprint 3 | US-030 | As a developer, I want to navigate analysis results using dashboard tabs. | Should | US-021 | Vaishnavi Goud | Closed
Sprint 4 | Sprint 4 | US-031 | As a developer, I want to validate the complete bug analysis workflow. | Must | US-030 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-032 | As a developer, I want to test different bug report formats. | Must | US-031 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-033 | As a developer, I want to validate bug triage results. | Must | US-031 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-034 | As a developer, I want to validate root cause and duplicate detection. | Must | US-025, US-026 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-035 | As a developer, I want to validate recommended fixes. | Must | US-027 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-036 | As a developer, I want to perform end-to-end integration testing. | Must | US-031 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-037 | As a developer, I want to fix defects found during testing. | Must | US-036 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-038 | As a developer, I want to verify dashboard usability and performance. | Should | US-030 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-039 | As a developer, I want to prepare project documentation. | Should | US-037 | Vaishnavi Goud | Open
Sprint 4 | Sprint 4 | US-040 | As a developer, I want to complete final system validation. | Must | US-039 | Vaishnavi Goud | Open
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 301 | 8 | 10 | 41 | 33 | 26 | 28 | 23 | 24 | 25 | 28 | 26 | 26 | 20 | 16
SPRINT 1 BACKLOG
US-001 | T1 | Study defect analysis workflows | 2026-06-30 | 2026-07-03 | Vaishnavi goud | Research | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2 | Design system architecture and agent flow. | 2026-07-01 | 2026-07-04 | Vaishnavi goud | Research | Completed | 5 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3 | Study bug report and stack trace structures | 2026-07-02 | 2026-07-04 | Vaishnavi goud | Research | Completed | 4 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4 | Design overall system architecture | 2026-07-03 | 2026-07-05 | Vaishnavi goud | Architecture | Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5 | Define agent responsibilities and orchestration flow | 2026-07-03 | 2026-07-05 | Vaishnavi goud | Architecture | Completed | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6 | Design knowledge base data model | 2026-07-04 | 2026-07-06 | Vaishnavi goud | Database Design | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T7 | Develop bug report submission interface | 2026-07-05 | 2026-07-07 | Vaishnavi goud | UI Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-008 | T8 | Develop bug report and stack trace upload API | 2026-07-06 | 2026-07-08 | Vaishnavi goud | BackendDevelopment | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0
US-009 | T9 | Seed historical defect datasets | 2026-07-07 | 2026-07-08 | Vaishnavi goud | Knowledge Base | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
US-010 | T10 | Implement chunking and embedding generation | 2026-07-08 | 2026-07-09 | Vaishnavi goud | RAG Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0
US-011 | T11 | Implement vector store indexing | 2026-07-09 | 2026-07-09 | Vaishnavi goud | RAG Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0
US-012 | T12 | Test submission module and knowledge base | 2026-07-09 | 2026-07-09 | Vaishnavi goud | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
US-013 | T1 | Design Triage Agent classification logic | 2026-07-10 | 2026-07-11 | Vaishnavi goud | AI Development | Completed | 5 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T2 | Implement severity and priority classification | 2026-07-11 | 2026-07-12 | Vaishnavi goud | AI Development | Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T3 | Implement affected component detection | 2026-07-12 | 2026-07-12 | Vaishnavi goud | AI Development | Completed | 5 | 0 | 0 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T4 | Add confidence scoring and reasoning | 2026-07-13 | 2026-07-13 | Vaishnavi goud | AI Development | Completed | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T5 | Parse stack traces and error messages | 2026-07-14 | 2026-07-15 | Vaishnavi goud | Log Analysis | Completed | 6 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T6 | Identify exception type and failure point | 2026-07-15 | 2026-07-16 | Vaishnavi goud | Log Analysis | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | T7 | Identify affected code paths | 2026-07-16 | 2026-07-17 | Vaishnavi goud | Log Analysis | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T8 | Implement multi-agent orchestration | 2026-07-17 | 2026-07-18 | Vaishnavi goud | BackenDevelopment | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T9 | Pass agent outputs to downstream agents | 2026-07-18 | 2026-07-19 | Vaishnavi goud | Integration | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-022 | T10 | Test agents with varied bug report formats | 2026-07-19 | 2026-07-20 | Vaishnavi goud | Testing | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
US-023 | T11 | Measure Triage and Log Analysis accuracy | 2026-07-20 | 2026-07-21 | Vaishnavi goud | Validation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
US-024 | T12 | Fix issues and finalize agent outputs | 2026-07-21 | 2026-07-21 | Vaishnavi goud | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
US-025 | T1 | Retrieve relevant historical bugs | 2026-07-22 | 2026-07-22 | Vaishnavi goud | RAG Development | Completed | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | T2 | Build Root Cause Agent prompt | 2026-07-22 | 2026-07-23 | Vaishnavi goud | AI Development | Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-027 | T3 | Generate root cause with confidence and evidence. | 2026-07-23 | 2026-07-23 | Vaishnavi goud | AI Development | Completed | 8 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-028 | T4 | Prepare search input for duplicate detection | 2026-07-23 | 2026-07-24 | Vaishnavi goud | BackenDevelopment | Completed | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-029 | T5 | Perform semantic similarity search | 2026-07-24 | 2026-07-24 | Vaishnavi goud | AI Development | Completed | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
US-030 | T6 | Display duplicate bugs with similarity scores | 2026-07-24 | 2026-07-25 | Vaishnavi goud | FrontenDevelopment | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
US-031 | T7 | Collect context for remediation recommendations | 2026-07-25 | 2026-07-25 | Vaishnavi goud | BackenDevelopment | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-032 | T8 | Design remediation prompt | 2026-07-25 | 2026-07-26 | Vaishnavi goud | AI Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
US-033 | T9 | Generate actionable fix recommendations | 2026-07-26 | 2026-07-27 | Vaishnavi goud | AI Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 8 | 0 | 0
US-034 | T10 | Design structured findings dashboard layout | 2026-07-27 | 2026-07-28 | Vaishnavi goud | UI Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-035 | T11 | Display all analysis results. | 2026-07-28 | 2026-07-29 | Vaishnavi goud | FrontenDevelopment | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
US-036 | T12 | Integrate and test all analysis outputs | 2026-07-29 | 2026-07-30 | Vaishnavi goud | Integration Testing | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
US-037 | T1 | Develop defect pattern analytics module | 2026-07-31 | 2026-07-31 | Vaishnavi goud | AnalyticDevelopment | Completed | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-038 | T2 | Identify recurring bug patterns. | 2026-07-31 | 2026-08-01 | Vaishnavi goud | Data Analytics | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-039 | T3 | Display defect trends, severities and root causes | 2026-08-01 | 2026-08-01 | Vaishnavi goud | FrontenDevelopment | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-040 | T4 | Implement knowledge base growth mechanism | 2026-08-02 | 2026-08-02 | Vaishnavi goud | BackenDevelopment | Completed | 8 | 0 | 2 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-041 | T5 | Store verified resolved bugs in vector database | 2026-08-03 | 2026-08-03 | Vaishnavi goud | RAG Development | Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-042 | T6 | Conduct end-to-end testing across varied bugtypes | 2026-08-04 | 2026-08-05 | Vaishnavi goud | Testing | Completed | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-043 | T7 | Validate agent and duplicate detection accuracy. | 2026-08-05 | 2026-08-06 | Vaishnavi goud | Validation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-044 | T8 | Validate recommendation relevance | 2026-08-06 | 2026-08-07 | Vaishnavi goud | Testing | Completed | 6 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-045 | T9 | Prepare technical documentation and user guide | 2026-08-07 | 2026-08-08 | Vaishnavi goud | Documentation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
US-046 | T10 | Prepare project report with results and future work | 2026-08-08 | 2026-08-09 | Vaishnavi goud | Documentation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 8 | 0 | 0 | 6 | 0
US-047 | T11 | Prepare final demonstration. | 2026-08-09 | 2026-08-10 | Vaishnavi goud | Demonstration | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-048 | T12 | Perform final system validation and project review | 2026-08-10 | 2026-08-11 | Vaishnavi goud | Final Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial project structure and repository setup were pending. | Created the project repository and configured the development environment.
Sprint 1 | Day 2 | Bug submission workflow required design clarification. | Finalized the bug submission interface and workflow.
Sprint 1 | Day 3 | Text input validation for bug reports was incomplete. | Added validation for bug descriptions, stack traces, and error logs.
Sprint 1 | Day 4 | File upload functionality needed support for multiple format | Implemented file upload for bug reports and log files successfully.
Sprint 1 | Day 5 | Public datasets were available in different formats. | Cleaned and organized Mozilla, Apache, and Eclipse datasets from Kaggle.
Sprint 1 | Day 6 | Historical bug data needed a common storage structure. | Built a historical defect knowledge base with standardized records.
Sprint 1 | Day 7 | Large bug reports affected document processing. | Applied document chunking for efficient processing.
Sprint 1 | Day 8 | Embedding generation required preprocessing of text. | Generated embeddings after cleaning and chunking the documents.
Sprint 1 | Day 9 | Efficient similarity search was not available. | Created a vector store index for semantic retrieval.
Sprint 1 | Day 10 | Retrieved documents required verification for relevance. | Validated indexed documents and improved retrieval quality.
Sprint 1 | Day 11 | Minor inconsistencies were found in uploaded bug records. | Corrected dataset formatting and removed duplicate entries.
Sprint 1 | Day 12 | No major impediments. | Reviewed completed modules and prepared project documentation.
Sprint 1 | Day 13 | Needed to verify integration of all completed modules. | Tested bug submission, knowledge base, chunking, embeddings, and indexing together.
Sprint 1 | Day 14 | No major impediments. Sprint ready for review. | Completed Sprint 1 review and documented the completed features.
Sprint 2 | Day 15 | Triage agent workflow required design finalization. | Designed the triage agent workflow and finalized the classification process.
Sprint 2 | Day 16 | Severity classification logic needed validation. | Implemented severity classification for Critical, High, Medium, and Low bugs.
Sprint 2 | Day 17 | Priority prediction and affected component mapping were incomplete. | . Added priority prediction and affected component identification.
Sprint 2 | Day 18 | Confidence scoring required evaluation criteria. | Generated confidence scores with reasoning for triage results.
Sprint 2 | Day 19 | Stack trace parsing required additional implementation. | Developed stack trace parsing for bug reports and error logs.
Sprint 2 | Day 20 | Error message analysis needed exception detection. | Implemented exception detection and failure point identification.
Sprint 2 | Day 21 | Failure point identification required structured processing. | . Generated structured output with affected code path details.
Sprint 2 | Day 22 | Multi-agent orchestration required agent integration. | . Integrated Triage and Log Analysis agents into the orchestration pipeline.
Sprint 2 | Day 23 | Agent outputs required downstream context integration. | Passed agent outputs as context to downstream analysis modules.
Sprint 2 | Day 24 | Validation required diverse bug report formats. | Validated agent performance using diverse bug reports and error types.
Sprint 2 | Day 25 | Minor inconsistencies were found in agent predictions. | Refined classification and parsing logic to improve prediction accuracy.
Sprint 2 | Day 26 | Final verification of Sprint 2 deliverables was pending. | Completed Sprint 2 review and documented the implemented features.
Sprint 3 | Day 27 | Root cause analysis needed prompt refinement. | Refined the root cause prompt.
Sprint 3 | Day 28 | Historical bug retrieval returned less relevant results. | Improved historical bug retrieval.
Sprint 3 | Day 29 | Confidence scores were inconsistent. | Adjusted confidence scoring logic.
Sprint 3 | Day 30 | Supporting evidence was not displayed correctly. | Updated evidence display mapping.
Sprint 3 | Day 31 | Duplicate detection returned unrelated matches. | Improved semantic similarity filtering.
Sprint 3 | Day 32 | Similarity scores needed validation. | Validated similarity thresholds.
Sprint 3 | Day 33 | Historical resolution details were incomplete. | Updated retrieval for resolution summaries.
Sprint 3 | Day 34 | Remediation recommendations were too generic. | Enhanced remediation prompt.
Sprint 3 | Day 35 | Fix recommendations needed better context. | Added historical and root cause context.
Sprint 3 | Day 36 | Dashboard layout required refinement. | Refined dashboard layout.
Sprint 3 | Day 37 | Root cause results were not displayed clearly. | Added structured root cause display.
Sprint 3 | Day 38 | Duplicate results needed better formatting. | Improved duplicate result formatting.
Sprint 3 | Day 39 | Remediation output formatting was inconsistent. | Standardized remediation output.
Sprint 3 | Day 40 | Minor dashboard UI issues were identified. | Fixed dashboard UI issues.
Sprint 4 | Day 41 | Integration between analysis modules needed testing. | Tested module integration.
Sprint 4 | Day 42 | Defect analytics data required cleaning. | Cleaned defect analytics data.
Sprint 4 | Day 43 | Recurring bug patterns were difficult to identify. | Implemented bug pattern grouping.
Sprint 4 | Day 44 | Component-wise defect counts needed validation. | Standardized component names.
Sprint 4 | Day 45 | Analytics dashboard needed additional visualizations. | Added analytics visualizations.
Sprint 4 | Day 46 | Knowledge base growth workflow needed implementation. | Implemented knowledge base update workflow.
Sprint 4 | Day 47 | Resolved bugs required verification before storage. | Added resolved bug verification.
Sprint 4 | Day 48 | Vector database updates needed validation. | Validated vector database updates.
Sprint 4 | Day 49 | End-to-end testing revealed integration issues. | Fixed integration issues.
Sprint 4 | Day 50 | Different stack trace formats produced inconsistent results. | Tested multiple stack trace formats.
Sprint 4 | Day 51 | Accuracy metrics required additional test cases. | Expanded test cases and calculated accuracy metrics.
Sprint 4 | Day 52 | Documentation required additional updates. | Updated project documentation.
Sprint 4 | Day 53 | Project report needed final result details. | Finalized project report.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-30 | 2026-07-09 | Vaishnavi Goud | Review system architecture before backend implementation. | Starting backend development without planning the module flow. | Maintaining clean and modular backend code. | Finalized system architecture before module implementation
2 | Sprint 1 | 2026-06-30 | 2026-07-09 | Vaishnavi Goud | Design the Bug Submission UI before implementation. | Making UI changes without validating user requirements. | Keeping the interface simple and user-friendly. | Completed system architecture and backend implementation
3 | Sprint 1 | 2026-06-30 | 2026-07-09 | Vaishnavi Goud | Validate datasets before building the knowledge base. | Importing raw datasets without preprocessing. | Maintaining well-structured and organized datasets. | Implemented backend modules as planned
4 | Sprint 1 | 2026-06-30 | 2026-07-09 | Vaishnavi Goud | Test the RAG pipeline after each implementation stage. | Waiting until the end of the sprint to test all modules. | Verifying retrieval results after every major update. | Completed backend implementation successfully
5 | Sprint 1 | 2026-06-30 | 2026-07-09 | Vaishnavi Goud | Discuss module dependencies during daily stand-up meetings. | Working on dependent modules without team coordination. | Sharing daily progress and updating project documentation. | Finalized backend module implementation
6 | Sprint 2 | 2026-07-10 | 2026-07-21 | Vaishnavi Goud | Validate triage predictions with different bug types. | Relying on a single bug format for testing. | Improve agent classification accuracy. | Tested triage classification across different bug types.
7 | Sprint 2 | 2026-07-10 | 2026-07-21 | Vaishnavi Goud | Validate stack-trace parsing with different error formats. | Testing only simple error messages. | Maintain structured log analysis output. | Validated stack-trace parsing with varied error formats.
8 | Sprint 2 | 2026-07-10 | 2026-07-21 | Vaishnavi Goud | Test agent communication after every integration. | Integrating agents without intermediate validation. | Monitor the multi-agent workflow. | Verified data flow between Triage and Log Analysis agents.
9 | Sprint 2 | 2026-07-10 | 2026-07-21 | Vaishnavi Goud | Record accuracy observations during testing. | Depending only on manual verification. | Report defects with clear evidence. | Recorded accuracy results and corrected incorrect predictions.
10 | Sprint 2 | 2026-07-10 | 2026-07-21 | Vaishnavi Goud | Review integration dependencies during stand-ups. | Delaying integration testing until the sprint end. | Conduct regular integration reviews. | Reviewed integration dependencies during sprint meetings.
11 | Sprint 3 | 2026-07-22 | 2026-07-30 | Vaishnavi Goud | Validate root-cause results using historical evidence. | Accepting root-cause results without supporting evidence. | Improve RAG retrieval quality. | Verified root-cause results using historical evidence.
12 | Sprint 3 | 2026-07-22 | 2026-07-30 | Vaishnavi Goud | Test duplicate detection with similar bug reports. | Relying only on exact text matching for duplicates. | Use semantic similarity for duplicate detection. | Tested duplicate detection using semantic similarity scores.
13 | Sprint 3 | 2026-07-22 | 2026-07-30 | Vaishnavi Goud | Validate remediation recommendations against historical fixes. | Generating recommendations without sufficient context. | Use verified historical resolutions. | Refined remediation recommendations using historical fixes.
14 | Sprint 3 | 2026-07-22 | 2026-07-30 | Vaishnavi Goud | Test the complete dashboard after every UI change. | Displaying raw or incomplete agent outputs. | Maintain a clear and structured dashboard. | Added structured dashboard sections for agent outputs.
15 | Sprint 3 | 2026-07-22 | 2026-07-30 | Vaishnavi Goud | Perform complete pipeline integration testing. | Testing agents independently without full pipeline validation. | Conduct regular integration testing. | Performed complete pipeline integration testing.
16 | Sprint 4 | 2026-07-31 | 2026-08-11 | Vaishnavi Goud | Analyze recurring defect patterns and trends. | Reviewing bugs only individually. | Monitor defect categories and components. | Implemented defect pattern analytics for recurring issues.
17 | Sprint 4 | 2026-07-31 | 2026-08-11 | Vaishnavi Goud | Validate resolved bugs before adding them to the knowledge base. | Adding unverified bug resolutions to the knowledge base. | Maintain high-quality historical data. | Added verified resolved bugs to the knowledge base.
18 | Sprint 4 | 2026-07-31 | 2026-08-11 | Vaishnavi Goud | Perform end-to-end testing with varied bug types. | Testing only individual modules. | Validate agent accuracy and recommendations. | Conducted end-to-end testing with multiple bug formats.
19 | Sprint 4 | 2026-07-31 | 2026-08-11 | Vaishnavi Goud | Prepare documentation alongside final development. | Postponing documentation until the final day. | Record testing observations and results. | Prepared technical documentation and testing reports.
20 | Sprint 4 | 2026-07-31 | 2026-08-11 | Vaishnavi Goud | Rehearse the final demonstration with complete submissions. | Considering the project complete without full pipeline validation. | Review project progress and risks. | Processed five bug submissions and prepared the final demonstration.