## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Engineer | 2026-07-08 | Unsupported file formats are accepted during bug report upload. | Sprint 1 | Backend team | Funtional | Added file type validation for uploads. | 2026-07-09 | closed | verified by QA
2 | QA Engineer | 2026-07-09 | Empty bug reports are submitted through direct paste. | Sprint 1 | Backend team | Validation | Implemented mandatory input validation. | 2026-07-10 | closed | validation working correctly
3 | AI Engineer | 2026-07-10 | Stack trace parser misses nested exception details. | Sprint 1 | AI Team | Parsing | Enhanced stack trace parsing logic. | 2026-07-11 | open | requires further testing
4 | Data Engineer | 2026-07-11 | Duplicate bug records are found during knowledge base creation. | Sprint 1 | Data team | Data | Removed duplicate records before indexing. | 2026-07-12 | closed | dataset cleaned successfully
5 | QA Engineer | 2026-07-12 | Similar bug retrieval returns low-relevance results. | Sprint 1 | AI team | AI model | Optimized embedding and retrieval settings. | 2026-07-13 | open | accuracy evaluation in progress
6 | QA Engineer | 2026-07-10 | Triage Agent assigns incorrect severity. | Sprint 2 | AI Team | AI Model | Refined severity classification rules. | 2026-07-12 | Closed | Verified
7 | QA Engineer | 2026-07-12 | Incorrect priority assigned to critical bugs. | Sprint 2 | AI Team | AI Model | Updated priority classification logic. | 2026-07-14 | Closed | Verified
8 | QA Engineer | 2026-07-15 | Log Analysis fails to identify exception type. | Sprint 2 | AI Team | AI Model | Improved stack trace parsing. | 2026-07-17 | Closed | Verified
9 | Backend Developer | 2026-07-17 | Agent outputs are not combined correctly. | Sprint 2 | Backend Team | Integration | Fixed multi-agent orchestration flow. | 2026-07-19 | Closed | Completed
10 | QA Engineer | 2026-07-19 | Agent accuracy varies for different bug formats. | Sprint 2 | AI Team | AI Model | Tested agents using varied bug datasets. | 2026-07-21 | Open | Testing required
11 | QA Engineer | 2026-07-22 | Root Cause Agent generates incorrect root cause. | Sprint 3 | AI Team | AI Model | Refined root cause prompt and RAG context. | 2026-07-24 | Closed | Verified
12 | QA Engineer | 2026-07-24 | Duplicate Detection returns unrelated bugs. | Sprint 3 | AI Team | AI Model | Tuned similarity threshold. | 2026-07-26 | Open | Testing required
13 | QA Engineer | 2026-07-26 | Similarity scores are not displayed correctly. | Sprint 3 | Frontend Team | UI | Updated duplicate results display. | 2026-07-27 | Closed | Verified
14 | QA Engineer | 2026-07-27 | Remediation Agent gives generic recommendations. | Sprint 3 | AI Team | AI Model | Added historical resolutions to context. | 2026-07-29 | Open | Needs improvement
15 | Frontend Developer | 2026-07-29 | Some agent results are missing from dashboard. | Sprint 3 | Frontend Team | UI | Added Root Cause, Duplicate and Remediation sections. | 2026-07-30 | Closed | Verified
16 | QA Engineer | 2026-07-31 | Defect analytics does not show recurring patterns. | Sprint 4 | AI Team | Analytics | Updated defect pattern analysis logic. | 2026-08-02 | Closed | Verified
17 | QA Engineer | 2026-08-02 | Frequent affected components are not displayed. | Sprint 4 | AI Team | Analytics | Added component frequency analysis. | 2026-08-04 | Closed | Verified
18 | Backend Developer | 2026-08-04 | Resolved bugs are not added to knowledge base. | Sprint 4 | Backend Team | Database | Implemented knowledge base update mechanism. | 2026-08-06 | Closed | Verified
19 | QA Engineer | 2026-08-06 | End-to-end pipeline fails for some bug formats. | Sprint 4 | QA Team | Integration | Performed end-to-end testing. | 2026-08-08 | Open | Testing required
20 | QA Engineer | 2026-08-08 | Documentation is missing setup details. | Sprint 4 | Entire Team | Documentation | Updated technical documentation and user guide. | 2026-08-10 | Closed | Completed
21 | QA Engineer | 2026-08-10 | Complete pipeline needs final demonstration. | Sprint 4 | Entire Team | Functional | Processed five different bug submissions. | 2026-08-11 | Closed | Completed
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50